## 2026
序号 Item | 是否要录入CRM | 履约商机号 BO No. | 国家 Country | 客户 Client | 项目名称 Peoject No. | 商机类型/产品线 BO Type/Product Line | 商机金额 BO Amount（USD） | 项目进展和任务 Project Process&Task | 结果 Result | 商机负责人 BO Owner | 保函 Guarantee Issued or Not | 合同签约 Contract Singed or Not | 总部订单号 HQ Order No. | 生产-FAT-发货 Production-FAT-Shipment | 回款 Payment Collection
1 | 否 | O3744 | DR | EDEESTE | EDEESTE-GC-C-2024-0025 | 投标Tender/配用电 Metering | 21397635.8861 | 1. Collect the 100% payment urgently!!! -Evelyn | Win | Evelyn | Performance Guanrantee: valid till 2025.12.05, already been cancelled. | Signed: EDEESTE-GC-C-2024-0025 | PWDO250004 | EDEESTE has receied the goods. | 100% TT OA 60days. We have forwarded the invoice on 2025.09.12, so the overdue date was 2025.11.12, need to collect the payment urgently!!!
2 | 否 | LYO0271 | DR | E&SG-EDEESTE | EDEESTE-CCC-LPN-2023-0012 | 投标Tender/配用电 Metering | 6437854.5 | EDEESTE has received 1st batch, 2nd batch was under customs clearance. 3rd batch will not started production till 1st batch payment is collected. 1. 1st batch payment collection (6 invoice: 2026.03.20-2026.04.05). - Hsia/Bessie | Win | Hsia | / | Signed | PWDO250005 | EDEESTE has received 1st batch, 2nd batch was under customs clearance. 3rd batch will not started production till 1st batch payment is collected. | 20% DP has been received. 1st batch 80% OA: $1153739.28; 2nd batch 80% OA: $1153739.28; 3rd batch 80% OA: $947580.69; 4th batch 80% OA: $947580.69; 5th batch 80% OA: $947580.69.
3 | 否 | O2868 | DR | SEER SOLAR | SEER SOLAR INVERTER PURCHASE FROM LIVOLTEK | 直采Direct Purchase/新能源 New Energy | 247660 | 1. Collect the overdue payment $135116.00 urgently!!! - Evelyn 2. Apply the Sinousre loss on 2026.03.20 if still not collect the overdue payment on this day. -Bessie 3. How to handle the rest stock qty in HQ warehouse? -Evelyn | Win | Evelyn | / | Singed | PWDO250010 | SEER has received the 1st batch. The rest qty is still waiting for SEER's new order coming to be shipped together. | 1st batch rest payment $135116.00, overdue since 2026.01.22, Sinosure loss claim deadline 2026.03.20.
4 | 否 | O7024 | DR | NAFTEX-EDESUR | EDESUR-CCC-LPN-2024-0040 | 投标Tender/配用电 Metering | 604152.5 | ETA: 2026.03.15 | Win | Evelyn | / | Signed: NAF-20250919EDS | PWDO250016 | FAT has finished. B/L date: 2026.01.28 ETA: 2026.03.15 | 20% DP has been received, 80% TT OA 60days.
5 | 否 | LYO1179 | DR | EDESUR 采集器 | EDESUR-CCC-PEPU-2025-0007 | 投标Tender/配用电 Metering | 982010 | 1. Collect the 80% payment at the beginning of April 2026. -Evelyn | Win | Evelyn | / | Signed: 0385-2025 | PWDO250019+0020 | EDESUR has recevied the goods. | 20% DP has been received, 80% TT OA 60days. We have forwarded the invoice on 2026.02.04, so the overdue date was 2026.04.04, need to collect the payment urgently!!!
6 | 否 | LYO1131 | DR | EDESUR G3 | EDESUR-CCC-LPN-2025-0034 | 投标Tender/配用电 Metering | 1575289.2 | ETA: 2026.03.09 | Win | Evelyn | Performance Guanrantee: valid till | Signed: 0446-2025 | PWDO250021 | FAT has finished. B/L date: 2026.01.28 ETA: 2026.03.09 | 100% TT OA 60days.
7 | 否 | LYO1495 | DR | EDESUR 指定G3 | EDESUR-CCC-PEPU-2025-0023 | 投标Tender/配用电 Metering | 2945340.27 | ETA: 2026.03.31 | Win | Evelyn | DP Guanrantee: valid till; Performance Guanrantee: valid till | Signed: 0434-2025 | PWDO250022 | FAT has finished. B/L date: 2026.02.26 ETA: 2026.03.31 | 20% DP has been received, 80% TT OA 60days.
8 | 是 | LYO35040 | DR | EDENORTE 紧急采购 | EDENORTE-MAE-PEEN-2025-0004 | 投标Tender/配用电 Metering | 170694.08 | 1. Contract need to be singed urgently!!! -Evelyn 2. 20% down payment+1st batch 80% payment need to be collected urgently!!! -Evelyn | Win | Evelyn | DP Guanrantee: valid till; Performance Guanrantee: valid till | Not Signed | PWDO250023+0024 | 1st batch: B/L date: ETA: 2nd batch: B/L date: ETA: | 20% DP, 80% TT OA 60days. 20% down payment+1st batch 80% payment need to be collected urgently!!
9 | 否 | LYO0567 | DR | EDESUR LTE圆表 | EDESUR-CCC-LPN-2025-0016 | 投标Tender/配用电 Metering | 13128174.89 | 1st batch: B/L date: ETA: 2nd+3rd batch FAT: start from 2026.05.06 4th batch: production still not arranged | Win | Evelyn | DP Guanrantee: valid till; Performance Guanrantee: valid till | Signed: 0450-2025 | PWDO250025+PWDO260001+0004 | 1st batch: B/L date: ETA: 2nd+3rd batch FAT: start from 2026.05.06 4th batch: production still not arranged | 20% DP has been received, 80% TT OA 60days.
10 | 是 |  | DR | EDESUR 加密盒 | EDESUR-CCC-PEPU-2025-0033 | 投标Tender/配用电 Metering | 14380 | Goods are under purchase. | Win | Evelyn | / | Signed: 0470-2025 | PWDO260003 | Goods are under purchase. | 100% TT OA.
11 | 是 | LYO48233 | DR | NAFTEX-EDEESTE G3 | EDEESTE MAE-PEEN-2025-0003 | 投标Tender/配用电 Metering | 3881014.6701 | EDEESTE G3招标，2025.12.18截标，我方作为供应商，由NAFTEX投标，已中标。 需考虑分批发货等方案来解决NAFTEX回款风险问题。 | Win | Evelyn | /
12 | 是 | LYO72422 | DR | EDEESTE LTE圆表 | EDEESTE-CCC-LPN-2025-0019 | 投标Tender/配用电 Metering | 5407406.68 | EDEESTE LTE圆表招标，2026.02.04截标，我方直接投标。 | Under Evaluation | Evelyn
13 | 是 | LYO99981 | DR | EDENORTE指定插拔表和采集器 | EDENORTE-CCC-PEPU-2025-0080 | 投标Tender/配用电 Metering | 135416.8 | EDENORTE 插拔表和采集器指定招标，2026.01.13截标，我方直接投标，已中标，已开履约保函。 | Win | Evelyn | Performance Guanrantee: valid till 2027.03.12
14 | 是 | LYO64367 | DR | EDEESTE 两年运维 | EDEESTE-CCC-PEPU-2025-0057 | 投标Tender/配用电 Metering | 70608.4 | EDEESTE 两年运维招标，2025.12.18截标，我方直接投标，已中标。 | Win | Evelyn | /
15 | 是 |  | DR | CEPM |  | 投标Tender/配用电 Metering
16 | 是 |  | DR | 世行 |  | 投标Tender/配用电 Metering
17 | 是 |  | DR | 智慧路灯 |  | 投标Tender/配用电 Metering
18 | 是 |  | DR | TERLINI 光伏路灯 | FIDEICOMISO-CCC-LPN-2026-0001 | 投标Tender/新能源 New Energy | 300000 | 我方作为供应商，代理投标，LOT 1-4全投，2026.03.16截标。 | Bidding | Evelyn
19 | 是 |  | DR | TERLINI 水表 |  | 投标Tender/水务Water Meter |  | 我方作为供应商，代理投标，已中标100Ppcs DN50，50pcs DN80，30pcs DN100。 | Win | Hsia
20 | 是 |  | DR | TERLINI 电磁流量计 | INAPA-CCC-LPN-2025-0028 | 投标Tender/水务Water Meter | 160290 | 我方作为供应商，代理投标，已中标50pcs电磁流量计。 | Win | Hsia
21 | 是 |  | JM | JPS G3 | JPS G3 PURCHASE | 投标Tender/配用电 Metering | 496775 | 已根据客户要求完成最终版修改报价，预计3月底客户会下发PO。 | Under Evaluation | Hsia
22 | 是 | LYO76650 | JM | JPS 单相重合器 | JPS 1P Recloser RFP | 投标Tender/配用电 Metering | 354000 | 我方直接投标，2026.02.11截标，需要跟进评标进展。 | Under Evaluation | Hsia
23 | 是 |  | JM | JPS 运维 | JPS Maintenance | 投标Tender/配用电 Metering | 74379 | JPS年度运维报价，2026.01.01-2026.12.31，需要尽快让电力局确认下PO和付款。 | Under Evaluation | Hsia
Note on H2: HEQ063: CURRENCY: DOP